## Roadmap
NFT Platform — Implementation Plan
Task tracker · 4 phases · 39 tasks · Companion to Architecture v5
ID | Task | Phase | Effort | Depends on | Risk | Status | Owner | Start | End | Notes / Exit criteria
Phase 1 — Foundation
Infrastructure · Schema · Polygon + TON adapters · Normalizer · State updater · Projections · API · Reorg handler
P1-01 | Postgres schema baseline migration | Phase 1 | M (3-7d) | — | Medium | Todo |  |  |  | 7 core schemas: ref, ingest, ledger, catalog, market, projection, system. All constraints and indexes from arch §9. user_content, social, scoring introduced in Phase 2.
P1-02 | ref tables seed data | Phase 1 | S (1-3d) | P1-01 | Low | Todo |  |  |  | Populate chains, networks, token_standards, marketplaces for target network.
P1-03 | Redis + MinIO + Docker Compose | Phase 1 | S (1-3d) | — | Low | Todo |  |  |  | Local dev + prod compose. Redis Streams is the Phase 1 event bus; Redis is also used for cache/locks.
P1-04 | Event envelope schema & validation lib | Phase 1 | S (1-3d) | — | Medium | Todo |  |  |  | Canonical RawEvent as Pydantic model + JSON Schema. Frozen interface between adapters and normalizer. Include schema_version.
P1-05 | ChainAdapter base class & contract tests | Phase 1 | M (3-7d) | P1-04 | Medium | Todo |  |  |  | Abstract interface: fetch_blocks, parse_raw_events. Contract tests: schema validation, sub_index completeness, delta conservation, source_event_id stability, empty deltas for non-transfers.
P1-06 | Polygon + TON adapters | Phase 1 | XL (3w+) | P1-05 | High | Todo |  |  |  | Implement both adapters in Phase 1: Polygon (ERC-721/1155 + marketplace events) and TON (TEP-62 + GetGems). Cover: Transfer, TransferBatch (or TON equivalent batch semantics), Mint, Burn, Listing, Sale, Cancel. Record real mainnet tx fixtures. Both adapters must pass all contract tests. Address canonicalization per arch §3.
P1-07 | Block fetcher & ingest cursor | Phase 1 | M (3-7d) | P1-06 | Medium | Todo |  |  |  | fetch_blocks with retry, rate-limit, circuit breaker. Write cursor to system.sync_cursors after each successful batch. Never advance cursor past failed block.
P1-08 | Normalizer worker | Phase 1 | L (1-3w) | P1-04, P1-01 | High | Todo |  |  |  | UPSERT normalized_event_keys (source_event_id, sub_index) — handles reorg re-inclusion. Write normalized_events + deltas. Create catalog stubs via uuidv5. Publish to ledger.normalized.
P1-09 | applied_events idempotency pattern | Phase 1 | M (3-7d) | P1-01 | High | Todo |  |  |  | Reusable library. INSERT INTO applied_events ON CONFLICT DO NOTHING before every state mutation. Write all 3 idempotency tests (§16.3) before marking done.
P1-10 | State updater — ownership | Phase 1 | M (3-7d) | P1-08, P1-09 | High | Todo |  |  |  | Consume ledger.normalized. UPSERT ownership_current qty += delta. DELETE qty <= 0. Update finality_status on finalization. Publish ledger.ownership_changed.
P1-11 | State updater — listings & sales | Phase 1 | M (3-7d) | P1-10 | Medium | Todo |  |  |  | Handle listing, sale, cancel event_kinds. Update listings_current. Insert sales_history. Publish market.listing_changed, market.sale_recorded.
P1-12 | Projection pipeline — ownership_view | Phase 1 | M (3-7d) | P1-10 | Medium | Todo |  |  |  | Upsert projection.ownership_view with finality_status. Template for all other projections. Write idempotency test for this projection.
P1-13 | Projection pipeline — asset_cards & stats | Phase 1 | M (3-7d) | P1-12 | Medium | Todo |  |  |  | projection.asset_cards and collection_stats. Handle is_stub=true gracefully — show stub data, not errors.
P1-14 | Projection pipeline — portfolio & listings | Phase 1 | M (3-7d) | P1-13 | Low | Todo |  |  |  | projection.portfolio_assets and listing_cards. Remaining projections for minimal functional API.
P1-15 | Core API skeleton & auth module | Phase 1 | M (3-7d) | P1-01 | Low | Todo |  |  |  | FastAPI modular structure. Auth: API keys only (JWT deferred to Phase 2). Enforce from day 1: on-chain modules read only from projection.*. user_content and social read own tables.
P1-16 | API endpoints: ownership, catalog, market | Phase 1 | M (3-7d) | P1-14, P1-15 | Low | Todo |  |  |  | GET /assets/{id}, /assets/{id}/owners, /collections/{id}, /collections/{id}/listings. All responses include finality_status. Stubs return is_stub:true, not 404.
P1-17 | Outbox publisher | Phase 1 | M (3-7d) | P1-01 | Medium | Todo |  |  |  | Poll system.outbox_events WHERE published_at IS NULL. Publish to Redis Streams. Mark published_at. After 5 failures → system.dlq.
P1-18 | Metrics & structured logging | Phase 1 | M (3-7d) | P1-07, P1-10 | Medium | Todo |  |  |  | All metrics from arch §15. Structured log contract in all workers. 4 dashboards. Alert rules for dlq_depth and outbox_unpublished_count (any non-zero).
P1-19 | Reorg handler | Phase 1 | L (1-3w) | P1-10 | High | Todo |  |  |  | Detect reorg in adapter. Emit reorg_detected. Mark is_reverted=true (scoped). Recompute ownership_current for affected asset_ids only. Write all 5 reorg test scenarios from arch §16.2.
EXIT CRITERIA — P1 complete when all pass:
✓ Contract tests pass for both adapters (all 5 types from arch §16.5; 10 tests total)
✓ Idempotency tests pass: single delivery, concurrent delivery, partial failure recovery
✓ Reorg scenarios 1-5 from arch §16.2 pass against real Postgres
✓ End-to-end: chain event → API response with correct finality_status within SLA
✓ ownership_view reconciliation: 0 mismatches for sample of 100 assets
✓ Observability: pipeline lag dashboard visible, dlq_depth alert tested and firing
✓ Code review: no direct SQL joins between on-chain domain modules in API
EXIT CRITERIA — P1 complete when all pass:
✓ Contract tests pass for both adapters (all 5 types from arch §16.5; 10 tests total)
✓ Idempotency tests pass: single delivery, concurrent delivery, partial failure recovery
✓ Reorg scenarios 1-5 from arch §16.2 pass against real Postgres
✓ End-to-end: chain event → API response with correct finality_status within SLA
✓ ownership_view reconciliation: 0 mismatches for sample of 100 assets
✓ Observability: pipeline lag dashboard visible, dlq_depth alert tested and firing
✓ Code review: no direct SQL joins between on-chain domain modules in API
Phase 2 — Multi-Network & Intelligence
Additional adapters · Metadata pipeline · Scoring · ClickHouse · Semantic search
P2-01 | Additional chain adapters (third+) | Phase 2 | L per adp | P1 exit ✓ | High | Todo |  |  |  | Each additional adapter must pass all contract tests before connecting to normalizer.
P2-02 | Metadata pipeline | Phase 2 | M (3-7d) | P1 exit ✓ | Medium | Todo |  |  |  | Consume asset_created. Fetch URI, compute content_hash, create version on change. Timeouts: 30s/3 retries. Malformed JSON: log+skip+retry. Oversized >5MB: store ref only.
P2-03 | Trait extraction & rarity scoring | Phase 2 | M (3-7d) | P2-02 | Low | Todo |  |  |  | Parse traits from metadata. Compute rarity_rank and rarity_pct per trait within collection. Store in catalog.asset_traits. Update projection.asset_cards.
P2-04 | ClickHouse setup & CDC pipeline | Phase 2 | L (1-3w) | P1 exit ✓ | Medium | Todo |  |  |  | Deploy ClickHouse. CDC (Debezium) or export job for price_snapshots + sales_history. Postgres retains 30d hot partition. Workers never write to ClickHouse directly.
P2-05 | Scoring pipeline — asset scores | Phase 2 | M (3-7d) | P2-03 | Medium | Todo |  |  |  | composite_score = rarity + liquidity + demand. Versioned via scoring_runs. Store in asset_scores. Update projection.asset_cards.composite_score and trending_assets.
P2-06 | Scoring pipeline — collector scores | Phase 2 | M (3-7d) | P2-05 | Low | Todo |  |  |  | portfolio_value_usd, diversity_score, activity_score per account. Update projection.portfolio_assets with estimated_value_usd.
P2-07 | Text embeddings & pgvector search | Phase 2 | L (1-3w) | P2-03 | Medium | Todo |  |  |  | Deploy semantic-encoder. Generate embeddings on metadata update. HNSW index on is_current=true. Hybrid search in search_docs. Expose /search endpoint.
P2-08 | API: scores, trending, search | Phase 2 | M (3-7d) | P2-05, P2-07 | Low | Todo |  |  |  | GET /assets/{id}/score, /collections/{id}/trending, /search?q=. Collection stats backed by ClickHouse for volume.
P2-09 | Reconciliation job | Phase 2 | M (3-7d) | P1 exit ✓ | Low | Todo |  |  |  | Scheduled hourly (staging) / daily (prod). Sample 1000 assets. Compare projection vs ground truth. Results to system.reconciliation_runs. Alert if mismatch_rate > 0.1%.
P2-10 | Metadata re-fetch scheduler | Phase 2 | M (3-7d) | P2-02 | Low | Todo |  |  |  | Periodic re-fetch for all assets. Check content_hash. After N failures → mark metadata_unreachable, stop retrying, surface in API.
P2-11 | Visual embeddings (parallelizable) | Phase 2 | M (3-7d) | P2-07 | Low | Todo |  |  |  | Image embeddings for visual similarity search. Runs in background. Separate model_version from text embeddings.
P2-12 | user_content module | Phase 2 | M (3-7d) | P1-15 | Low | Todo |  |  |  | Wallet linking + verification. Folder CRUD with rules + exclusions. Compose layouts and positions. Reads user_content.* directly.
P2-13 | social module | Phase 2 | M (3-7d) | P2-12 | Low | Todo |  |  |  | Comments (threaded), reactions, notifications triggered by ownership/market events.
P2-14 | Price oracle integration | Phase 2 | S (1-3d) | P1 exit ✓ | Low | Todo |  |  |  | Fetch exchange rates for native tokens → USD. All price_usd fields include rate timestamp. Alert if rate > 5min stale.
EXIT CRITERIA — P2 complete when all pass:
✓ All contract tests pass for each new adapter
✓ stub_assets_total trends to zero within 10min for test batch of 1000 assets
✓ ClickHouse: 90-day floor price history query < 100ms for collection with 50k sales
✓ Search: precision@10 > 0.7 on test query set
✓ Reconciliation job: 0 mismatches for 3 consecutive daily runs across all networks
✓ Per-network lag metrics visible for all active networks
EXIT CRITERIA — P2 complete when all pass:
✓ All contract tests pass for each new adapter
✓ stub_assets_total trends to zero within 10min for test batch of 1000 assets
✓ ClickHouse: 90-day floor price history query < 100ms for collection with 50k sales
✓ Search: precision@10 > 0.7 on test query set
✓ Reconciliation job: 0 mismatches for 3 consecutive daily runs across all networks
✓ Per-network lag metrics visible for all active networks
Phase 3 — Production Hardening
Kafka · Full reorg suite · Personalization · Canary SLA · Backfill
P3-01 | Kafka / Redpanda migration | Phase 3 | L (1-3w) | P2 exit ✓ | Medium | Todo |  |  |  | Replace Redis Streams. Envelope schema frozen for this — no app logic changes. Dual-write 24h before cutover. Validate consumer counts match.
P3-02 | Full reorg test suite | Phase 3 | L (1-3w) | P2 exit ✓ | High | Todo |  |  |  | All 5 scenarios from arch §16.2 for each network. Network-specific: TON masterchain delay, EVM uncle blocks, Solana fork. Automated simulation in staging.
P3-03 | Personalization engine | Phase 3 | L (1-3w) | P2-07, P2-06 | Medium | Todo |  |  |  | User preference vectors from ownership + viewing history + folders. Blend personalization with relevance + rarity + liquidity in trending and search ranking.
P3-04 | Qdrant migration (conditional) | Phase 3 | M (3-7d) | P3-01 | Low | Todo |  |  |  | Only if p99 semantic search > 200ms. Backend swap via abstraction layer. Validate: same precision@10, lower p99, no hybrid search regression.
P3-05 | Advanced collection analytics | Phase 3 | L (1-3w) | P2-04 | Medium | Todo |  |  |  | ClickHouse-backed: wash trading detection, price manipulation signals, whale concentration. API endpoints + collection_stats projection.
P3-06 | Achievements system | Phase 3 | M (3-7d) | P2-13 | Low | Todo |  |  |  | achievements_catalog + user_achievements. Triggered by events. Notification-worker sends achievement notifications.
P3-07 | API rate limiting & quota | Phase 3 | M (3-7d) | P1-15 | Low | Todo |  |  |  | Per-API-key rate limiting via Redis. Quota tiers. X-RateLimit-Remaining headers. Graceful degradation: serve stale projection data under DB pressure.
P3-08 | SLA monitoring & canary | Phase 3 | M (3-7d) | P2 exit ✓ | Medium | Todo |  |  |  | Automate all freshness SLA checks from arch §17.2. Synthetic canary transaction every 5min. Alert if canary misses SLA window.
P3-09 | Backfill tooling | Phase 3 | L (1-3w) | P2 exit ✓ | Medium | Todo |  |  |  | CLI to backfill from configured start block. Uses same normalizer/state-updater pipeline. Idempotent: re-runnable without duplicates.
P3-10 | Staging environment parity | Phase 3 | M (3-7d) | P3-01 | Low | Todo |  |  |  | Staging mirrors prod schema + pipeline exactly. Nightly reconciliation staging vs prod. Real chain data. All reorg tests run in staging.
EXIT CRITERIA — P3 complete when all pass:
✓ Kafka: 0 message loss during 72h dual-write. Consumer lag < 1000 msgs/partition steady state
✓ Full reorg test suite passes for all supported networks
✓ Canary SLA: 99.5% of canary transactions visible in API within SLA window over 7 days
✓ p99 API latency < 200ms for projection-backed endpoints under 2x peak load
EXIT CRITERIA — P3 complete when all pass:
✓ Kafka: 0 message loss during 72h dual-write. Consumer lag < 1000 msgs/partition steady state
✓ Full reorg test suite passes for all supported networks
✓ Canary SLA: 99.5% of canary transactions visible in API within SLA window over 7 days
✓ p99 API latency < 200ms for projection-backed endpoints under 2x peak load
Phase 4 — Scale (only where measured)
No speculative scaling. Each task requires a profiler trace identifying the bottleneck.
P4-01 | Ingest horizontal scaling by network | Phase 4 | M (3-7d) | Measured lag | Low | Todo |  |  |  | Only if ingest_lag_seconds alert fires consistently. Shard adapter: partition block range, each with own cursor. Normalizer handles out-of-order via UPSERT.
P4-02 | Projection pipeline parallelization | Phase 4 | M (3-7d) | Measured lag | Low | Todo |  |  |  | Only if projection_lag_seconds fires consistently. Partition pipeline by asset_id/collection_id hash. applied_events prevents cross-partition conflicts.
P4-03 | normalized_events partition count increase | Phase 4 | L (1-3w) | Measured query | Medium | Todo |  |  |  | Only if a HASH partition exceeds 100M rows. Double partition count (8→16). Requires data migration + maintenance window.
P4-04 | Hot-path service extraction | Phase 4 | XL (3w+) | Measured contention | Medium | Todo |  |  |  | Last resort only. Profile first, extract second. The modular monolith should handle significant scale before this.
P4-05 | Read replica routing | Phase 4 | M (3-7d) | Primary CPU >70% | Medium | Todo |  |  |  | Add Postgres read replicas. Route projection.* reads to replicas. Writes stay on primary. Monitor replication lag.
P4-06 | applied_events archival | Phase 4 | S (1-3d) | INSERT latency | Low | Todo |  |  |  | Only if applied_events > 100M rows and INSERT latency degrades. Archive rows >90d to cold table. Primary retains recent rows for fast idempotency checks.
EXIT CRITERIA — P3 complete when all pass:
✓ Kafka: 0 message loss during 72h dual-write. Consumer lag < 1000 msgs/partition steady state
✓ Full reorg test suite passes for all supported networks
✓ Canary SLA: 99.5% of canary transactions visible in API within SLA window over 7 days
✓ p99 API latency < 200ms for projection-backed endpoints under 2x peak load

## Risk Register
Risk Register
# | Risk | Phase | Impact | Mitigation
1 | Dedup bug in normalizer silently drops events | P1 | Critical | Contract test: same event twice → exactly 1 normalized_events row. Run before any production data flows through.
2 | applied_events missing from a worker → double balance on replay | P1 | Critical | Code review gate: any function that mutates ledger state must use applied_events. Consider a linter rule.
3 | Solana addresses lower()-corrupted in adapter | P2 | Critical | Address canonicalization unit tests per network family. Fixture tests with known Solana addresses that differ only by case.
4 | ERC-1155 TransferBatch: sub_index omitted → batch collapse | P1 | Critical | Contract test: batch expansion with 1, 10, 100-item batches. Assert sub_index sequence is contiguous from "0".
5 | Reorg re-inclusion: is_reverted stays true → missing ownership | P1 | High | Reorg test scenario 2 (re-inclusion) must pass before Phase 1 exit. UPSERT on normalized_event_keys updates is_reverted.
6 | Projection diverges from ledger silently | P1+ | High | Reconciliation job (P2-09) samples 1000 assets hourly. Canary SLA monitor (P3-08) detects end-to-end failures within minutes.
7 | ClickHouse sync lag causes stale analytics served as fresh | P2 | Medium | Include CDC lag as a monitored metric. Surface data_as_of timestamp in all analytics API responses.
8 | Metadata URI permanently broken → stuck stubs forever | P2 | Medium | After N failures: mark metadata_unreachable, stop retrying, surface is_stub + metadata_unreachable in API response.
9 | Kafka migration loses messages in transition window | P3 | High | Dual-write Redis Streams + Kafka for 24h. Validate message counts match on both sides before cutting Redis Streams off.
10 | Premature Phase 4 scaling adds complexity without benefit | P4 | Medium | Hard rule: no Phase 4 task starts without a profiler trace showing the specific bottleneck being addressed.

## Decision Log
Decision Log
# | Decision | Chosen | Rejected | Rationale
1 | API architecture | Modular monolith | Microservices | Domains tightly coupled. Small team. Velocity > isolation at this stage.
2 | Event bus — Phase 1 | Redis Streams | Kafka from day 1 | Lower ops overhead. Envelope schema frozen for future migration.
3 | Event bus — Phase 3 | Kafka / Redpanda | Stay on Redis Streams | At-least-once guarantees, consumer groups, replay semantics.
4 | normalized_events partitioning | HASH(network_id) | Time partition | Time partition breaks global unique PK constraint in Postgres.
5 | Dedup strategy | Unpartitioned keys table | UNIQUE on partitioned tbl | Postgres cannot enforce cross-partition UNIQUE without partition key.
6 | Worker idempotency mechanism | applied_events table (DB) | In-memory / Redis dedup | DB transaction guarantees. Survives worker restart. Auditable.
7 | Surrogate ID generation | uuidv5 from natural key | Auto-increment | Deterministic. Enables forward references. Eliminates FK race conditions.
8 | Address canonicalization | Canonical string at ingestion | lower() at query time | Canonical form varies by network family. lower() corrupts Solana addresses.
9 | Embedding storage (Phase 2) | pgvector | Qdrant | Simpler ops. Abstraction allows later migration if p99 > 200ms.
10 | ClickHouse rollout timing | Phase 2 | Phase 3 | sales_history and price_snapshots outgrow Postgres faster than other tables.